Deliverable 1.3 - Los Angeles County DPW Kick-Off Meeting Notes and

Action Item Summary

March 7, 2005

Attendees:

Kimley-Horn: Melissa Hewitt; Terry Murphy; Jean Fares; Kevin Thomas

Los Angeles County: Jane White; Maged Soliman; Marty Amundson

| Meeting notes | Action Items |
| --- | --- |
| Final submittal currently scheduled for August, 2005. LA County noted that the PS&E is the critical element of the project and need to be fast tracked. Kimley-Horn agreed to review and revise the schedule to complete the design as quickly as possible. |  |
| Keeping the PS&E moving quickly is the number one priority for LA County. LA County would like project status meetings to be on a product deliverable basis. | KHA to identify project milestones for proposed progress meetings |
| KHA offered to add the controller manufacturer and a controller recommendation to the cabinet inventory under Task 3.3 based on our previous field work in order to expedite the task. | Draft controller recommendation (KHA) |
| The County noted that the following guidelines apply to controller upgrades. If LACO IV firmware is to be used (with any central control system), then: All 170 controllers are recommended to be upgraded to a 170ATC controller. All 170E controllers manufactured by McCain Traffic Supply, Safetrans, or IDC/US Traffic, with a minimum of 2 rear C-ports, are recommended to be upgraded with a QUADUART HC-11 CPU board. All 170E controllers NOT manufactured by McCain Traffic Supply, Safetrans, or IDC/US Traffic are recommended to be upgraded to a 170ATC controller. |  |
| Industry, Walnut, Unincorporated LA County, controllers will use LACO IV firmware with KITS. Firmware is a critical path item as it will determine the controller upgrade portion of the PS&E. Pomona will continue to use Bitran. | County will follow-up with San Dimas, Claremont, La Verne, and Diamond Bar for controller program use. |
| Marty to obtain base plans/ as-builts for KHA. | As-built Collection (County) |
| Maged to obtain utility plans, starting with the location for proposed interconnect along Colima from Stoner creek Rd to Nogales St, and send to KHA. | Utility Plan Collection (County) |
| LA County to provide KHA with digitized files of Colima Rd from Stoner Creek Rd to Nogales St for interconnect design. | Digitized files of Colima Rd (County) |
| Critical path item: confirm locations of all field elements. | KHA to double check locations of existing and proposed interconnect, mark-up on GIS map. KHA to have telephone feed points marked up on the GIS map prior to the next County meeting. |
| KHA to deliver phase 1 reports this week: revised Concept Design Report, CCTV prioritization tech memo, and O&M report. Meet with County to confirm field element locations. | KHA to deliver phase 1 reports |
| KHA to set up kick-off meeting with each City after the CCTV locations have been finalized. Include City IT staff and City Engineer staff in kickoff meeting. | Set up City kick-off meetings (KHA) |
| KHA to decide to use County bucket truck or rent a bucket truck for CCTV survey. KHA to finalize decision with Maged. | KHA to follow-up |
| Plan deliverables will be in six packages: Unincorporated LA County/City of Industry/City of Walnut City of Diamond Bar City of Pomona City of Claremont City of San Dimas City of La Verne |  |
| KHA to obtain phone drop address locations under Task 2.1 and submit them to Maged. Maged to coordinate phone drop locations with SBC. | Phone drop address locations to County 03-25-05 (KHA) |
| Marty to provide a list of all intersections that will need advanced loops to be split for counting purposes. | Advanced loop intersection list (County) |
| LA County to provide KHA with a list of signal cabinets that are to be upgraded from 337 or Type P to 332 cabinets. | Signal cabinet upgrade list to KHA (County) |
| PS&E submittals are to go directly to Marty with a c.c. to Jane and Maged on the transmittal letter only. Allow 2 weeks for County review and turn around. |  |
| KHA to develop generic LCC/System architecture packets, obtain County approval, and bring to each City kick off meeting. | Develop LCC/System architecture packets (KHA) |
| KHA to develop a project FTP site and provide the link to LA County. | Develop project FTP site (KHA) |
| KHA requested Notice to Proceed on the following tasks at the meeting: Task 1: Project Management Task 2: Conduct Field Review Task 3: Field Review and Base plans Task 4-6: PS&E Task 8: Advanced Traffic Management System (ATMS) Task 9: LCC’s and TMC’s Task 10: Video Distribution Evaluation Please signify your concurrence that Kimley-Horn and Associates, Inc. is authorized to proceed with the above mentioned tasks by return e-mail for our records. |  |